## Sheet1
Faculty of Engineering Sciences & Technology
Task Management System
Supervised By Umer Chawla
Coordinated By Dr. Masoor Ebrahim
Planned Work
Month | Duration in weeks | Activity Name | Total Progress in %
January | Week 1 | Creating and Finalizing Timeline | 5%
Feburary | Week 2 | create Authentication API | 15%
| Week 3 | design Authentication Screens | 20%
| Week 4 | functionality of authentication screen | 25%
| Week 5 | creating task APIs for (Create update and delete task) | 30%
March | Week 6 | developing task screens UI and functionality | 35%
| Week 7 | creating expense APIs | 40%
| Week 8 | developing expnse screens UI and functionality | 50%
| Week 9 | creating communication API | 60%
April | Week 10 | developing communication screen UI and functionality | 70%
| Week 11 | attendence module Api and fuctionality | 80%
| Week 12 | Finalization and Reporting | 85%
| Week 13 | Testing | 95%
May | Week 14 | Final Presentation | 100%